## Checklist
Instructions: | Program:
1. Select Program | 2016 Floods - Homeowner Assistance Program
2. Filter "Include?" Column (F) for "Yes" only
3. Print Checklist, either to a printer, or to PDF
LOCD-DR Grant Implementation Checklist for:
2016 Floods - Homeowner Assistance Program
Action | Timing | Reference | Status | Include?
2.1 Grant and Project Approval |  |  |  | Yes
Receive CDBG-DR or CDBG-MIT allocation | Once | LOCD-DR |  | Yes
Receive notification of eligible programs | Once | LOCD-DR |  | Yes
Procure Project Administrator | Once | Chapter 4 |  | Yes
Execute contract with Project Administrator | Ongoing | Chapter 4 |  | Yes
Obtain citizen participation on programs/projects | Ongoing | Chapter 1 |  | Yes
Optional: Submit preliminary application; identify program areas | Once | Project Application |  | Yes
Receive approval of pre-application | Once | LOCD-DR |  | Yes
Procure Project Engineer/Architect, if required | Once | Chapter 4 |  | Yes
Execute contract with Project Engineer/Architect, if required | Once | Chapter 4 |  | Yes
Prepare & submit project application to the LOCD-DR | Ongoing | Project Application |  | Yes
Receive project approval from the LOCD-DR | Ongoing | LOCD-DR |  | Yes
Submit Request for Amendments no later than 90 days prior to the project expiration date | As needed | Chapter 1 |  | Yes
Execute change orders as needed | As needed | Chapter 1 |  | Yes
Submit change orders to LOCD-DR | As needed | Chapter 1 |  | Yes
2.2 Administrative Set-Up |  |  |  | Yes
Attend project Kick-off Meeting | Once | N/A |  | Yes
Develop Code of Conduct | Once | Chapter 4 |  | Yes
Establish Written Policies and Procedures |  |  |  | Yes
Develop Citizen Participation Plan | Once | Chapter 1 |  | Yes
Complaints procedures | Once | Chapter 1 |  | Yes
Monitoring plan | Once | Chapter 11 |  | Yes
Write and adopt a Procurement Policy to contain all federal requirements contained in 2 CFR 200.318-200.327 | Once | Chapter 4 |  | Yes
Voluntary Acquisition policy and procedures | Once | Chapter 9 |  | Yes
Property Management procedures | Once | Chapter 12 |  | Yes
Establish Internal Control System for Financial Management and develop financial management system | Once | Chapter 5 |  | Yes
Written policy manual specifying approval authority for financial transactions and guidelines for controlling expenditure | Once | Chapter 5 |  | Yes
Written procedures for recording of financial transactions | Once | Chapter 5 |  | Yes
Establish an accounting manual and a chart of accounts | Once | Chapter 5 |  | Yes
Establish hiring policies that ensure financial staff qualifications are equal to job responsibilities | Once | Chapter 5 |  | Yes
Establish records management filing system | Once | Chapter 3 |  | Yes
Complete and Submit CEA Support Documentation |  |  |  | Yes
Register for LaGov Vendor ID | Once | Chapter 5 |  | Yes
Complete and Return LaGov Electronic Funds Transfer (EFT) Enrollment form directly to OSRAP | Once | Chapter 5 |  | Yes
Submit CEA Contact Information Form (Exhibit 5-1) | Once | Chapter 5 |  | Yes
Submit IRS Form W-9 (if applicable) (Exhibit 5-2) | Once | Chapter 5 |  | Yes
Submit Authorized Signature Form (Exhibit 5-3) (Submit an up-to-date copy as needed) | Once | Chapter 5 |  | Yes
Submit Board Resolution (Submit an up-to-date copy as needed) | Once | Chapter 5 |  | Yes
Submit Proof of required insurances (Submit an up-to-date copy as needed) | Once | Chapter 5 |  | Yes
Submit Proof of active registration status from Sam.gov (Submit an up-to-date copy as needed) | Once | Chapter 5 |  | Yes
Submit HUD Form 2880 (Exhibit 5-5) | Once | Chapter 5 |  | Yes
2.3 Construction Management |  |  |  | Yes
Execute contract documents and applicable bonding and insurance requirements | As needed for all applicable Contracts | Chapter 1 Chapter 4 |  | Yes
Review the contract file and associated compliance files to ensure that documentation is complete | As needed for all applicable Contracts | Chapter 1 |  | Yes
Inform the prime contractor(s) of his/her responsibilities (via an optional pre-construction conference or other means of notification) | As needed for all applicable Contracts | Chapter 1 Chapter 8 |  | Yes
For any subcontractors not identified in the bid, obtain the data necessary to verify eligibility, signed required certifications, and written Section 3 (of the HUD Act of 1968) Compliance Plan | As needed for all applicable Contracts | Chapter 1 |  | Yes
Submit Verification form to the LOCD-DR | As needed for all applicable Contracts | Chapter 1 |  | Yes
Issue a Notice to Proceed to each prime contractor | As needed for all applicable Contracts | Chapter 1 |  | Yes
Check equal opportunity and labor standards compliance files prior to making partial payments | As needed for all applicable Contracts | Chapter 1 |  | Yes
Monitor contractor progress, make progress payments | As needed for all applicable Contracts | Chapter 1 |  | Yes
Perform a final inspection upon receipt of the contractor’s Final Request for Payment | As needed for all applicable Contracts | Chapter 1 |  | Yes
Receive all weekly payrolls and Statements of Compliance; resolve discrepancies | As needed for all applicable Contracts | Chapter 1 |  | Yes
Issue acceptance of work and final payment, less the retainage | As needed for all applicable Contracts | Chapter 1 |  | Yes
Prepare the Final Wage Compliance Report | As needed for all applicable Contracts | Chapter 1 Chapter 13 |  | Yes
Release the retainage upon the receipt of a clear lien certificate from the contractor | As needed for all applicable Contracts | Chapter 1 |  | Yes
Utilize the comprehensive Construction Contract Checklist (Exhibit 1-3) to ensure all steps are taken | As needed for all applicable Contracts | Chapter 1 |  | Yes
Achieve Green Building and Resilent Standards, as applicable | As applicable | Chapter 1 |  | Yes
2.4 Record Keeping and Reporting |  |  |  | Yes
All records should be kept according to requirements within Chapter 3 and Program Policies | Ongoing | Chapter 3 |  | Yes
Submit required reports to LOCD-DR as described in CEA and Program Policies | Monthly/Quarterly | Chapter 1 |  | Yes
2.5 Procurement |  |  |  | Yes
Write and adopt procedures for procurement transactions prior to securing contract services | Once | Chapter 4 |  | Yes
Establish a contract administration system | Once | Chapter 4 |  | Yes
Advertise as an Equal Opportunity Employer | Once | Chapter 4 |  | Yes
Document efforts to solicit minority and women's businesses | Once | Chapter 4 |  | Yes
Verify contractor clearance for awarding a construction, consulting, and engineering contracts | Ongoing | Chapter 4 Chapter 8 |  | Yes
Make sure that all contractors advertise as Equal Opportunity Employers | Ongoing | Chapter 4 Chapter 7 |  | Yes
Maintain records sufficient enough to document the significant history of a procurement | Ongoing | Chapter 4 Chapter 3 |  | Yes
Make sure that all contractors and subcontractors develop written employment policies and procedures | Ongoing | Chapter 7 |  | Yes
Determine appropriate procurement method to procure materials or services | As needed | Chapter 4 |  | Yes
Include performance measures and penalties in procured contracts | Ongoing | Chapter 4 |  | Yes
Include period of performance or date of completion in procured contracts | Ongoing | Chapter 4 |  | Yes
Perform an analysis of lease versus purchase alternative to determine most economical option | As needed | Chapter 5 |  | Yes
Procurement by Micro-purchase |  |  |  | Yes
Perform price analysis | As needed | Chapter 4 |  | Yes
Procurement by Small Purchase |  |  |  | Yes
Receive at least three quotes | As needed | Chapter 4 |  | Yes
Perform price analysis | As needed | Chapter 4 |  | Yes
Maintain written documentation for the basis of selecting the winning firm | As needed | Chapter 4 |  | Yes
Execute appropriate contract (Purchase Order or Fixed Price) | As needed | Chapter 4 |  | Yes
Submit a Notice of Contract Award to LOCD-DR | Within 30 days of awarding contract | Chapter 4 |  | Yes
Procurement by Sealed Bids |  |  |  | Yes
Submit final plans, specifications, and cost estimate (for construction only) (Technical bid specifications must be stamped by an architect or engineer registered in Louisiana) | As needed | Chapter 4 |  | Yes
Obtain approval from LOCD-DR to advertise for bids | As needed | Chapter 4 |  | Yes
Publish an advertisement for bids (“invitation for bids”) | As needed | Chapter 4 |  | Yes
Submit a copy of the publicized bid advertisement, including the publication date, to LOCD-DR | As needed | Chapter 4 |  | Yes
If bid documents are amended during the advertisement period, send addendum to all prospective bidders and LOCD-DR | As needed | Chapter 4 |  | Yes
Hold public bid opening at the time and place set in the advertisement for bids | As needed | Chapter 4 |  | Yes
Perform a written review and tabulation bids according to selection criteria | As needed | Chapter 4 |  | Yes
Contact LOCD-DR if the lowest bid received will exceed the amount of funds allocated for the project | As needed | Chapter 4 |  | Yes
Maintain written documentation for the basis of selecting the winning firm and rejecting any or all bids | As needed | Chapter 4 |  | Yes
Submit a certified and itemized bid tabulation to LOCD-DR | As needed | Chapter 4 |  | Yes
Perform cost/price analysis | As needed | Chapter 4 |  | Yes
Award a fixed price contract to the lowest responsive and responsible bidder within 45 days of bid opening | 45 days after bid opening | Chapter 4 |  | Yes
Submit a Notice of Contract Award to LOCD-DR | Within 30 days of awarding contract | Chapter 4 |  | Yes
Procurement by Competitive Proposals |  |  |  | Yes
Draft the RFP/RFQ for materials or services to be procured | As needed | Chapter 4 |  | Yes
Advertise the RFP/RFQ | As needed | Chapter 4 |  | Yes
Solicit responses to the RFP/RFQ from an adequate number of qualified sources | As needed | Chapter 4 |  | Yes
Conduct a technical evaluation of the proposals received | As needed | Chapter 4 |  | Yes
Maintain written documentation for the basis of selecting the winning firm and rejecting any or all proposals | As needed | Chapter 4 |  | Yes
Perform cost/price analysis | As needed | Chapter 4 |  | Yes
Award the appropriate contract to the firm with the winning proposal (cost reimbursement or fixed price contract only) | As needed | Chapter 4 |  | Yes
Submit a Notice of Contract Award to LOCD-DR | Within 30 days of awarding contract | Chapter 4 |  | Yes
Procurement by Noncompetitive Negotiation (Sole Source) |  |  |  | Yes
Draft the RFP/RFQ for materials or services to be procured | As needed | Chapter 4 |  | Yes
Advertise the RFP/RFQ | As needed | Chapter 4 |  | Yes
Solicit responses to the RFP/RFQ from an adequate number of qualified sources | As needed | Chapter 4 |  | Yes
Perform a cost analysis | As needed | Chapter 4 |  | Yes
Determine that competitive procurement is infeasible (See Chapter 4, Section 9.7) | As needed | Chapter 4 |  | Yes
Submit to LOCD-DR evidence of efforts to secure competition and a clear justification for sole source request; obtain written approval from LOCD-DR | As needed | Chapter 4 |  | Yes
2.6 Financial Audits and Monitoring |  |  |  | Yes
Submit a copy of the written engagement agreement to the Legislative Auditor of the State of Louisiana for approval of the engagement terms and conditions (only if an independent CPA is engaged to prepare an audit or compilation) | As needed | Chapter 5 |  | Yes
If $75,000 or less in revenue received, submit annual sworn financial statements | Annually | Chapter 5 |  | Yes
If more than $75,000 but less than $200,000 in revenue received, submit annual compilation of financial statements | Annually | Chapter 5 |  | Yes
If $200,000 or more but $500,000 or less in revenue received, submit an annual review of financial statements, accompanied by an attestation report | Annually | Chapter 5 |  | Yes
If more than $500,000 in revenue is received within a fiscal year, submit an audit | Annually | Chapter 5 |  | Yes
If $1,000,000 or more in federal funds are expended within a fiscal year, conduct a Single Audit Note: Office of Management and Budget (OMB) increased the threshold from $750,000 to $1,000,000 for fiscal years beginning October 1, 2024 | Annually | Chapter 5 |  | Yes
Submit data collection form and reporting package of the annual Single Audit to the Federal Audit Clearinghouse (FAC) | Annually | Chapter 5 |  | Yes
Within 30 days after receipt of auditor’s report, submit final copies to the FAC and LOCD-DR | Annually | Chapter 5 |  | Yes
Respond in writing to the LOCD-DR regarding any findings of noncompliance | As needed | Chapter 5 |  | Yes
2.7 Financial Responsibilities |  |  |  | Yes
Request approval from LOCD-DR if a single item leased or purchased exceeds $10,000 | As needed | Chapter 5 |  | Yes
Submit an approved Indirect Cost Proposal prior to charging indirect costs to the grant | Once | Chapter 5 |  | Yes
Review Request for Payment to ensure all funds are allowable and for approved eligible activities | As needed | Chapter 5 |  | Yes
Collect Support Documentation - Vendor invoices must be on vendor letterhead - Timesheets must detail hours worked and detailed duties performed | As needed | Chapter 5 |  | Yes
Separate Costs into correct category - Activity Delivery Costs - Direct Project Costs - Planning Costs - Admin Costs | As needed | Chapter 5 |  | Yes
Person designated on the Authorized Signature Form must sign the Request for Payment | As needed | Chapter 5 |  | Yes
Submit Request for Payment Form with supporting documentation to LOCD-DR for reimbursement | As needed | Chapter 5 |  | Yes
Return program income to LOCD-DR, unless LOCD-DR provides an exception | As needed | Chapter 5 |  | Yes
2.8 Environmental Review |  |  |  | Yes
Aggregate (group together) all individual activities which are related either geographically or functionally, or are logical part of a composite of contemplated action | Ongoing | Chapter 6 |  | Yes
Create and maintain an Environmental Review Record (ERR) for all aggregated activities | Ongoing | Chapter 6 |  | Yes
Exempt Activities |  |  |  | Yes
Prepare and submit the executed "Environmental Review for Activity/Project that is Exempt or Categorically Excluded Not Subject to Section 58.5" to the LOCD-DR | Ongoing | Chapter 6 |  | Yes
Obligate or incur the "Exempt Activity" costs (soft costs) and request payment of funds | Ongoing | Chapter 6 |  | Yes
Categorically Excluded Activities Not Subject to 58.5 (CENST) |  |  |  | Yes
Prepare and submit the executed “Environmental Review for Activity/Project that is Exempt or Categorically Excluded Not Subject to Section 58.5” to the LOCD-DR | As needed | Chapter 6 |  | Yes
Receive confirmation from the LOCD-DR (NTP if applicable) | As needed | Chapter 6 |  | Yes
Begin to obligate or incur ONLY costs cleared in CENST and request payment of funds | As needed | Chapter 6 |  | Yes
Categorically Excluded Activities Subject to 58.5 (CEST) |  |  |  | Yes
Prepare and submit the executed "Environmental Review for Activity/Project that is Categorically Excluded Subject to Section 58.5" to the LOCD-DR | As needed | Chapter 6 |  | Yes
Prepare and Publish a “Notice of Intent to Request a Release of Funds” (NOI/RROF) | As needed | Chapter 6 |  | Yes
Submit the Request for Release of Funds (RROF) and Proof of Publication of the NOI/RROF to the LOCD-DR | As needed | Chapter 6 |  | Yes
Receive the Authority to Use Grant Funds (AUGF) and NTP from the LOCD-DR | As needed | Chapter 6 |  | Yes
Begin to obligate or incur costs and request payment of funds after all NTP stipulations are met | As needed | Chapter 6 |  | Yes
Environmental Assessment |  |  |  | Yes
Prepare and Submit the Environmental Assessment (EA) | As needed | Chapter 6 |  | Yes
Post/publish combined notice of FONSI/RROF | As needed | Chapter 6 |  | Yes
Complete and submit to LOCD-DR the Request for Release of Funds (HUD Form 7015.15) | As needed | Chapter 6 |  | Yes
Submit Publication Proof of FONSI/RROF to LOCD-DR | As needed | Chapter 6 |  | Yes
Receive the Authority to Use Grant Funds (AUGF) and NTP from the LOCD-DR | As needed | Chapter 6 |  | Yes
Begin to obligate or incur costs and request payment of funds after all NTP stipulations are met | As needed | Chapter 6 |  | Yes
2.9 Civil Rights |  |  |  | Yes
Employment |  |  |  | Yes
Publish an annual statement of nondiscrimination and/or include such statement in any publicity on a CDBG-DR or CDBG-MIT program | Annually | Chapter 7 |  | Yes
Develop Plan to ensure compliance with Section 3 of the HUD Act of 1968 plan | Once | Chapter 7 |  | Yes
Display Equal Opportunity posters prominently | Ongoing | Chapter 7 |  | Yes
Notify LOCD-DR if complaints are registered | As needed | Chapter 7 |  | Yes
Contracting |  |  |  | Yes
Advertise as an equal opportunity employer in bid solicitations | Ongoing | Chapter 7 |  | Yes
Solicit bids from minority, women and locally owned businesses | Ongoing | Chapter 7 |  | Yes
Maintain a list of locally owned businesses that were awarded contracts | Ongoing | Chapter 7 |  | Yes
Require a Section 3 (of the HUD Act of 1968) clause in all contracts | Ongoing | Chapter 7 |  | Yes
Inform contractors of equal opportunity (via an optional pre- construction conference or other means of notification) | Ongoing | Chapter 7 |  | Yes
Require contractor to submit monthly utilization reports | Ongoing | Chapter 7 |  | Yes
Monitor contractor compliance at work site | Ongoing | Chapter 7 |  | Yes
Fair Housing |  |  |  | Yes
Disseminate information concerning housing services and activities to agencies and organizations which routinely provide services to protected groups | Ongoing | Chapter 7 |  | Yes
Evaluate criteria for selecting recipients of housing assistance for any discriminatory effects | Once | Chapter 7 |  | Yes
Participate in Fair Housing Activities | Ongoing | Chapter 7 |  | Yes
Conduct at least one Fair Housing activity during the project period | Once | Chapter 7 |  | Yes
Section 504 of the Rehabilitation Act of 1973, as amended (29 U.S.C. 754)) |  |  |  | Yes
Publish a statement of compliance with Section 504 of the Rehabilitation Act of 1973, as amended (29 U.S.C. 754) and/or include such statement in any publicity on a CDBG-DR or CDBG-MIT program | Ongoing | Chapter 7 |  | Yes
Make available a TDD or equally effective method for communicating with hearing impaired persons | Once | Chapter 7 |  | Yes
Maintain Summary of Actions Taken to Achieve Compliance with Section 504 | Ongoing | Chapter 7 |  | Yes
Execute and submit Section 504 Assurance | Annually | Chapter 7 |  | Yes
Complete a self-evaluation of current policies and practices to determine if they meet the requirements of being accessible to individuals with disabilities within 6 months of grant award | Within 6 months of receiving grant award | Chapter 7 |  | Yes
Develop a transition plan for those areas which cannot be made accessible administratively | As needed | Chapter 7 |  | Yes
Complete construction activities identified in the transition plan | Within 3 years of completing self-evaluation | Chapter 7 |  | Yes
Section 3 of the HUD Act of 1968 |  |  |  | Yes
Include Section 3 clause in all Section 3 covered contracts | Ongoing | Chapter 7 |  | Yes
Employ efforts to assist in reaching Section 3 residents and businesses for employment opportunities | Ongoing | Chapter 7 |  | Yes
Employ efforts to assist in reaching Section 3 businesses for contracting opportunities | Ongoing | Chapter 7 |  | Yes
Maintain data to report compliance with Section 3 (of the HUD Act of 1968) as required | Ongoing | Chapter 7 |  | Yes
2.10 Labor (if applicable) |  |  |  | No
Designate a Labor Compliance Officer (LCO) | Once | Chapter 8 |  | No
Determine effective wage decision(s) | Once | Chapter 8 |  | No
Verify wage decision | Once | Chapter 8 |  | No
Ensure Prime Contractors clear subcontractors | As needed | Chapter 8 |  | No
Inform the prime contractor(s) of his/her responsibilities (via an optional pre-construction conference or other means of notification) | Ongoing | Chapter 1 Chapter 8 |  | No
Provide additional classifications, if needed | As needed | Chapter 8 |  | No
Conduct employee interviews and periodic field inspections to ensure labor compliance | Ongoing | Chapter 8 |  | No
Obtain notification from prime contractor of contract awards to any subcontractor prior to the subcontractor beginning work on the project | As needed | Chapter 8 |  | No
Ensure all payroll statements are properly submitted and reviewed | Ongoing | Chapter 8 |  | No
Notify prime contractor if back wages are required | As needed | Chapter 8 |  | No
Verify fringe benefits if problems are suspected | As needed | Chapter 8 |  | No
Document when no work is performed to reflect no payrolls received | As needed | Chapter 8 |  | No
Submit the Labor Standards Enforcement Report to LOCD-DR | As needed | Chapter 8 |  | No
Contact LOCD-DR if restitution is not paid within 30 days of the second notice of underpayment or if there is a disagreement regarding the finding of wages owed | As needed | Chapter 8 |  | No
Request approval from LOCD-DR if Force Account Labor is to be used | As needed | Chapter 8 |  | No
If Force Account Labor is used, request approval for equipment cost allocation (use-allowance or depreciation value) | As needed | Chapter 8 |  | No
Notify LOCD-DR if intentional falsification by a contractor is suspected | As needed | Chapter 8 |  | No
2.11 Voluntary Acquisition of Real Property |  |  |  | Yes
Prepare a formal, written Voluntary Acquisition Policy | Once | Chapter 9 |  | Yes
Publish a public notice | For each applicable property | Chapter 9 |  | Yes
Determine ownership | For each applicable property | Chapter 9 |  | Yes
Execute a professional services contract with an independent appraiser if appraisals are needed | For each applicable property | Chapter 9 |  | Yes
Formally invite the property owner to accompany the appraiser during inspection of the property | For each applicable property | Chapter 9 |  | Yes
Obtain an appraisal or written opinion | For each applicable property | Chapter 9 |  | Yes
Prepare and execute an Act of Sale | For each applicable property | Chapter 9 |  | Yes
Provide a Statement of Settlement Costs to owner | For each applicable property | Chapter 9 |  | Yes
Record any required documents | For each applicable property | Chapter 9 |  | Yes
2.12 Involuntary Acquisition of Real Property |  |  |  | No
Determine ownership | For each applicable property | Chapter 9 |  | No
Send Preliminary Acquisition Notice | For each applicable property | Chapter 9 |  | No
Send HUD “When a Public Agency Acquires your Property” brochure to owner | For each applicable property | Chapter 9 |  | No
Send local Voluntary Acquisition Policy to owner | For each applicable property | Chapter 9 |  | No
Execute a professional services contract with an independent appraiser if appraisals are needed | For each applicable property | Chapter 9 |  | No
Formally invite the property owner to accompany the appraiser during inspection of the property | For each applicable property | Chapter 9 |  | No
Determine if an appraisal is needed | For each applicable property | Chapter 9 |  | No
If yes, perform appraisal and review appraisal | For each applicable property | Chapter 9 |  | No
If no, obtain a written valuation of the property | For each applicable property | Chapter 9 |  | No
Prepare and send the Statement of Just Compensation | For each applicable property | Chapter 9 |  | No
Prepare and send the Offer to Purchase | For each applicable property | Chapter 9 |  | No
Conclude negotiations | For each applicable property | Chapter 9 |  | No
Obtain approval from the LOCD-DR to purchase property above the market value (if needed) | For each applicable property | Chapter 9 |  | No
Prepare and execute an Act of Sale | For each applicable property | Chapter 9 |  | No
Provide a Statement of Settlement Costs to owner | For each applicable property | Chapter 9 |  | No
For donated property, obtain a waiver of URA benefits from owner | For each applicable property | Chapter 9 |  | No
For expropriation proceedings, contact the LOCD-DR and submit required forms (including if the “Quick-Take” process is used) | For each applicable property | Chapter 9 |  | No
2.13 Residential Permanent Relocation |  |  |  | Yes
Provide Notice of Eligibility for Relocation Assistance | For each applicable property | Chapter 9 |  | Yes
Send a HUD “When a Public Agency Acquires your Property” brochure to owner | For each applicable property | Chapter 9 |  | Yes
Send a copy of the Grievance Procedure taken from the Subrecipient’s local Relocation Policy to owner | For each applicable property | Chapter 9 |  | Yes
Conduct interview and survey with each URA recipient | For each applicable property | Chapter 9 |  | Yes
Locate and inspect replacement housing | For each applicable property | Chapter 9 |  | Yes
Provide counseling and appropriate referrals to social service agencies | For each applicable property | Chapter 9 |  | Yes
Offer or pay for transportation (e.g., taxi, rental car) to inspect housing for all displaced persons | For each applicable property | Chapter 9 |  | Yes
Send 90-day Notice to Vacate | For each applicable property | Chapter 9 |  | Yes
Provide permanent relocation benefits | For each applicable property | Chapter 9 |  | Yes
2.14 Residential Temporary Relocation |  |  |  | Yes
Send Notice of Nondisplacement to tenant | For each applicable property | Chapter 9 |  | Yes
Determine if relocation is needed | For each applicable property | Chapter 9 |  | Yes
Send Temporary Relocation Notice | For each applicable property | Chapter 9 |  | Yes
Inspect temporary relocation unit | For each applicable property | Chapter 9 |  | Yes
Provide temporary relocation benefits | For each applicable property | Chapter 9 |  | Yes
2.15 Business Relocation |  |  |  | No
Provide General Information Notice to business to be displaced | For each applicable property | Chapter 9 |  | No
Send HUD Information Booklet, Relocation Assistance to Displaced Businesses, NPOs, and Farms (HUD 1043-CPD) | For each applicable property | Chapter 9 |  | No
Send Notice of Relocation Eligibility | For each applicable property | Chapter 9 |  | No
Provide business relocation benefits | For each applicable property | Chapter 9 |  | No
2.16 Lead-Based Paint, Asbestos, and Mold |  |  |  | Yes
Perform Lead-Based Paint assessment, as applicable | As applicable | Chapter 10 |  | Yes
Disclose Lead-Based Paint Hazards to tenants, as applicable | As applicable | Chapter 10 |  | Yes
Inspect structures and ensure demolition and/ or renovation practices comply with CAA and OSHA if asbestos is found and will be disturbed | As applicable | Chapter 10 |  | Yes
Follow guidelines established by the U.S. EPA regarding the identification and remediation of mold | As applicable | Chapter 10 |  | Yes
Ensure compliance with location construction code enforcement agencies for buildings containing mold | As applicable | Chapter 10 |  | Yes
2.17 Property Management |  |  |  | Yes
Obtain title to property | For all property acquired/ purchased | Chapter 12 |  | Yes
Maintain adequate records documenting the proper use of property | For all property acquired/ purchased | Chapter 12 |  | Yes
Conduct a physical inventory of the property at least once every two years, reconciling the results with the property records | For all property acquired/ purchased | Chapter 12 |  | Yes
Properly dispose of equipment | For all property acquired/ purchased | Chapter 12 |  | Yes
Document the proceeds of the sale of CDBG-DR or CDBG-MIT property as program income | For all property acquired/ purchased | Chapter 12 |  | Yes
Request approval from LOCD-DR to use equipment acquired with CDBG-DR or CDBG-MIT funds as a trade-in on replacement property | As Needed | Chapter 12 |  | Yes
Maintain Property Control Tracking log | Ongoing | Chapter 12 |  | Yes
2.18 Close-out |  |  |  | Yes
Receive final claims or invoices from your contractor(s) or subrecipient and close them out | Within 30 days of completion of each project/activity | Chapter 13 |  | Yes
Prepare Certificate of Completion forms and submit to LOCD-DR | For each project/activity | Chapter 13 |  | Yes
Submit Requests for Project Amendments to reallocate any unutilized funds | For each project/activity | Chapter 13 |  | Yes
Return Program Income to LOCD-DR | For each project/activity | Chapter 13 |  | Yes
Dispose of Property | For each project/activity | Chapter 13 |  | Yes
Prepare Activity Completion Report and submit to LOCD-DR | For each project/activity | Chapter 13 |  | Yes
Receive Conditional Close-out Letter from LOCD-DR if financial audit/compliance issue pending | For each project/activity | Chapter 13 |  | Yes
Submit to LOCD-DR all pending audits and resolve outstanding compliance issues, if applicable | For each project/activity | Chapter 13 |  | Yes
Receive Final Project Close-out Letter from the LOCD-DR | For each project/activity | Chapter 13 |  | Yes

## ProgramSelections (hidden)
Checklist Sections / Subsections | Hurricane Francine - Restore LA Homeowner Program | Hurricane Francine - Interim Housing Assistance | Hurricane Francine - Flood Insurance Assistance Program | 2020-2021 HSG - FMA-Swift (Non-Federal Share Match) | 2020-2021 HSG - Flood Insurance Program | 2020-2021 HSG - Housing Buyouts | 2020-2021 HSG - Interim Housing Assistance | 2020-2021 HSG - Middle-Market Loan Program (MMLP) | 2020-2021 HSG - Permanent Supportive Housing Program(PSHP) | 2020-2021 HSG - Rapid Rehousing Program | 2020-2021 HSG - Rental Restoration and Development (RRDP) | 2020-2021 HSG - Resilient Mixed Income Gap Funding Program (PRIME) | 2020-2021 HSG - Restore LA Homeowner Program | 2020-2021 HSG - Soft Second Mortgage Program | 2020-2021 HSG - Homeless and Housing Stability Development Program | 2020-2021 INF - HMGP Global Match Program | 2020-2021 INF - Local and Regional Watershed Projects and Program | 2020-2021 INF - Nonfederal Share Match Program | 2020-2021 INF - Resilient Communities Infrastructure Program | 2020-2021 ECR - Small Business Loan and Grant Program | 2016 Floods - Homeowner Assistance Program | 2016 Floods - RLHP Flood Insurance Assistance Program | 2016 Floods - RLHP Interim Housing Assistance Program | 2016 Floods - Neighborhood Landlord Rental Program | 2016 Floods - Neighborhood Landlord Program Phase II | 2016 Floods - Neighborhood Landlord Program Phase III | 2016 Floods - Multifamily Rental GAP Program | 2016 Floods - Piggyback Program | 2016 Floods - Permanent Supportive Housing Program | 2016 Floods - Rapid Rehousing Program | 2016 Floods - Resilient and Mixed Income Piggyback Program (PRIME) | 2016 Floods - Soft Second Mortgage Program | 2016 Floods - Safe Haven Program | 2016 Floods - Louisiana Military Dept- Affordable Rental Housing | 2016 Floods - Cypress at Ardendale- Affordable Rental Housing | 2016 Floods - Rural Repair and Rehabilitation Program | 2016 Floods - OCD CDBG Homeownership (OCHO) Pilot Program | 2016 Floods - Middle-Market Loan Program (MMLP) | 2016 Floods - Fast GAP A Program | 2016 Floods - Small Business Loan Program | 2016 Floods - Farm Recovery Program | 2016 Floods - Infrastructure Program (PA Match) | 2016 Floods - First Responders Public Services Program | 2016 Floods - PRO Louisiana Workforce Development | Watershed Initiative - Local and Regional Projects and Programs | Watershed Initiative - State Infrastructure and Housing | Watershed Initiative - State Economic Development and Resilience | Watershed Initiative - Non-Federal Cost Share Assistance | Watershed Initiative - Watershed Monitoring, Mapping, and Modeling | Watershed Initiative - Watershed Policy, Planning, and Local Capacity Assistance | NDR - Safe Haven Blue-Green Campus | ------------------------------------------------------ | All Items | Administration | HSG - Homeownership Assistance | HSG - Rental Assistance | HSG - Relocation payments and assistance | HSG - Buyout | HSG - Homeowner Rehab/Recon | HSG - Construction of Affordable Rental Housing | HSG - Construction of New Replacement Housing | INF - Construction / Reconstruction of Streets | INF - Construction / Reconstruction of Water Lift Stations | INF - Construction/reconstruction of water/sewer lines or systems | INF - Dike/dam/stream-river bank repairs | INF - Rehabilitation/reconstruction of public facilities / improvement | INF - Acquisition, construction,reconstruction of public facilities | Public Services | Planning | Code Enforcement | Economic Development
2.1 Grant and Project Approval | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
2.2 Administrative Set-Up | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Establish Written Policies and Procedures | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Complete and Submit CEA Support Documentation | Yes | No | No | Yes | No | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
2.3 Construction Management | No | No | No | No | No | Yes | No | Yes | No | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No
2.4 Record Keeping and Reporting | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
2.5 Procurement | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Procurement by Micro-purchase | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Procurement by Small Purchase | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Procurement by Sealed Bids | Yes | No | No | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No
Procurement by Competitive Proposals | Yes | No | No | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | Yes | Yes | No | Yes
Procurement by Noncompetitive Negotiation (Sole Source) | Yes | No | No | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | Yes
2.6 Financial Audits and Monitoring | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
2.7 Financial Responsibilities | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
2.8 Environmental Review | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Exempt Activities | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Categorically Excluded Activities Subject to 58.5 (CEST) | Yes | No | No | Yes | No | Yes | No | No | No | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes
Categorically Excluded Activities Not Subject to 58.5 (CENST) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Environmental Assessment | Yes | No | No | Yes | No | Yes | No | Yes | No | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes
2.9 Civil Rights | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Employment | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Contracting | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Fair Housing | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Section 504 of the Rehabilitation Act of 1973, as amended (29 U.S.C. 754)) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Section 3 of the HUD Act of 1968 | No | No | No | No | No | No | No | Yes | No | No | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes
2.10 Labor (if applicable) | No | No | No | No | No | No | No | Yes | No | No | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes
2.11 Voluntary Acquisition of Real Property | Yes | No | No | No | No | Yes | No | No | No | No | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | No | No | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes
2.12 Involuntary Acquisition of Real Property | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | Yes | Yes | No | Yes | No | No | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | Yes | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No
2.13 Residential Permanent Relocation | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No | No | Yes | No | No | No | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | Yes
2.14 Residential Temporary Relocation | Yes | Yes | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No | No | Yes | No | No | No | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | Yes | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | Yes
2.15 Business Relocation | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | Yes | Yes | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | Yes | Yes | No | No | No | Yes | No | No | No | No | No | No | No | No | Yes
2.16 Lead-Based Paint, Asbestos, and Mold | Yes | Yes | No | No | No | No | Yes | No | No | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | No | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes
2.17 Property Management | Yes | No | No | No | No | Yes | No | Yes | No | No | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes |  | Yes | No | No | No | No | Yes | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes
2.18 Close-out | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Conditional Close-out (for each project) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Final Close-out (for each project) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Subrecipient/CEA Close-out | No | No | No | Yes | No | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes

## Verified Checklists (hidden)
Programs | Manager | Verified By | Notes | Confirmed
2016 Floods - Cypress at Ardendale - Affordable Rental Housing | Danielle/Jill | LA | Sections 2.7, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab | Jill recently took over from Danielle, that's why it was submitted twice
2016 Floods - Fast GAP A Program | Jill | LA | Sections 2.7, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab | Acquisition added back after conversing with Jill
2016 Floods - Infrastructure Program (PA Match) | Kirsten | ID | Sections 2.1, 2.2 and 2.8 have a few "No"s added and questions, but this did not change the entire Section so nothing changed on Progam Selections Tab. Also Sections 2.13 and 2.14 changed to "No" when previously had listed "Yes". Kirsten listed as N/A
2016 Floods - Louisiana Military Dept - Affordable Rental Housing | Danielle | LA
2016 Floods - Middle-Market Loan Program (MMLP) | Jill | LA | Sections 2.7, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab
2016 Floods - Neighborhood Landlord Rental Program | Danielle | LA | Labor Sections changed "Yes" when previously had listed "No" | Action Plan has new construction as eligible activity
2016 Floods - Neighborhood Landlord Rental Program Phase II | Danielle | LA | Labor Sections changed "Yes" when previously had listed "No" | Action Plan has new construction as eligible activity
2016 Floods - Neighborhood Landlord Rental Program Phase III | Danielle | LA | Labor Sections changed "Yes" when previously had listed "No" | Action Plan has new construction as eligible activity
2016 Floods - Piggyback Program | Jill | LA | Sections 2.7, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab | Acquisition added back after conversing with Jill
2016 Floods - Resilient and Mixed Income Piggyback Program (PRIME) | Jill | LA | Sections 2.7, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab | Acquisition added back after conversing with Jill
2020-2021 HSG - FMA-Swift (Non-Federal Share Match) | Danielle | LA | Labor Sections changed "Yes" when previously had listed "No" | ID spoke with Danielle and she stated that elevation is involved
2020-2021 HSG - Middle-Market Loan Program (MMLP) | Jill | LA | Sections 2.2, 2.5, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab | Labor/Acquisition added back after conversing with Jill
2020-2021 HSG - Rental Restoration and Development (RRDP) | Danielle | LA
2020-2021 HSG - Resilient Mixed Income Gap Funding Program (PRIME) | Jill | LA | Sections 2.7, 2.9 have a few "No"s added, but not entire Section so nothing changed on ProgramSelections Tab
2021-2021 INF - Nonfederal Share Match Program | Kirsten | ID | Sections 2.1 and 2.2 have a few "No"s added, but this does not change the entire section so nothing changed on the Program Selections Tab
Watershed Initiative - Non-Federal Cost Share Assistance | Kirsten | ID
2020-2021 INF - HMGP Global Match Program | Kirsten | ID
2016 Floods - PRO Louisiana Workforce Development | Natalie | ID | Sections 2.1, 2.2. and 2.17 have a few "No"s added but not entire Section so nothing changed on Program Selections Tab. However, Sections 2.5 (Procurement by Sealed Bids and Procurement by Competitive Proposal), 2.9 (Contracting and Fair Housing), and 2.11 changed to "No" when previously had listed as "Yes" | After verifying with Natalie, the sections were changed to No's. According to Natalie, this program is paying college tuition; and for the procurement section, the micro, small purchase and non competitive section were left as "yes" because they will be purchasing simulators.
2016 Floods - Small Business Loan Program | Natalie | ID
2016 Floods - Safe Haven Program | Natalie | ID
2020-2021 INF - Resilient Communities Infrastructure Program | Matthew | ID
Watershed Initiative - Local and Regional Projects and Programs | Genea | ID | Sections 2.1, 2.2, 2.5, and 2.17 have a few "No"s added, but this does not change entire Section so nothing changed on ProgramSelections Tab
Watershed Initiative - State Infrastructure and Housing | Genea | ID | Sections 2.1, 2.2, 2.5, and 2.17 have a few "No"s added, but this does not change entire Section so nothing changed on ProgramSelections Tab
Watershed Initiative - Watershed Monitoring, Mapping, and Modeling | Genea | ID | Sections 2.1, 2.2, 2.5, and 2.8 have a few "No"s added, but this does not change entire Section so nothing changed on Program Selections Tab. However, 2.17 changed to "No" when previously had listed as "Yes"
Watershed Initiative - Watershed Policy, Planning, and Local Capacity | Genea | ID | Sections 2.1, 2.2, 2.5, and 2.8 have a few "No"s added, but this does not change entire Section so nothing changed on Program Selections Tab.
2020-2021 HSG - Restore LA Homeowner Program | Jill | GV | Sections 2.13 and 2.14 changed to No, everything else is the same. 2.17 was added as a Yes Property management due to LOCD has to maintain the propertys.
2016 Floods - RLHP Flood Insurance Assistance Program | Jill | GV