Exhibit 11-1

Sample Subrecipient Monitoring Plan

Revised May 2025

PLEASE NOTE

These are monitoring guidelines.

Subrecipients should obtain a thorough understanding of the concepts described within Chapter 11 of the Grant Implementation Manual prior to completing any monitoring. Subrecipients should then revise this Sample Monitoring Plan and the Checklists to meet their monitoring needs.

Contents

- Monitoring Overview	1

- Monitoring Checklist	2

- Types of Monitoring	2

- Monitoring Process	2

  - Risk Assessment and Monitoring Schedule	2

  - Execute Checklist	3

  - Monitoring Letter	3

  - Technical Assistance	4

  - Follow-up	4

# Monitoring Overview

has established this Monitoring Plan to:

(SUBRECIPIENT NAME)

  - Gauge the overall progress and effectiveness of the project implementation.

  - Serve as a management tool to identify issues that may compromise program integrity, funding, and service delivery for corrective action and resolution.

  - Serve as a technical assistance tool whereby the subrecipient identifies areas in which to strengthen program capacity and quality of service delivery.

has been identified as the Monitoring Coordinator for 	.

(MONITORING COORDINATOR NAME)	(SUBRECIPIENT NAME)

The Monitoring Coordinator is responsible for:

- Ensuring that a risk assessment is executed for all projects (attach completed Risk Assessment);

- Setting the Monitoring Schedule that prioritizes reviews based on risk (see Table 1);

- Ensuring proper documentation and tracking of all monitoring efforts;

- Notifying the LOCD-DR of severe issues;

- Engaging the LOCD-DR for necessary technical assistance; and,

- Ensuring Monitoring occurs as outlined within the Plan.

If the subrecipient has engaged an administrative consultant and the Subrecipient’s Monitoring Coordinator is the administrative consultant, the subrecipient must identify a contract administrator responsible for monitoring the administrative consultant.

List the contract administrator for each   	 administrative consultant procured:

Project Administration

The subrecipient is administering all projects without an administrative consultant  or subrecipient.	  ☐Yes	☐No

If yes, identify the Subrecipient staff responsible   	        for project administration:

The subrecipient is utilizing an administrative consultant to administer projects.	☐Yes	☐No

If yes, list the Administrative Consultant:

Projects administered by the consultant:

(List Project IDs)

The subrecipient is utilizing a subrecipient to administer projects.	  ☐Yes	    ☐No

If yes, list the subrecipient:

Projects administered by the subrecipient:

(List Project IDs)

Subrecipients who choose not to use the Checklists from the LOCD-DR Grant Implementation Manual to perform their monitoring should describe the Monitoring Tools they are using in this section. Otherwise, the references to the LOCD-DR Grant Implementation Manual described below are sufficient.

Monitoring Checklist

The Core Checklist (Exhibit 11-2 of the LOCD-DR Grant Implementation Manual) will be used to monitor Subrecipients.

The Project Checklist (Exhibit 11-3 of the LOCD-DR Grant Implementation Manual) will be used to review Subrecipient Projects.

The Contract Administration Checklist (Exhibit 11-4 of the Grant Implementation Manual) will be used to monitor any Administrative Consultants.

# Types of Monitoring

At least one onsite review should be conducted of all projects prior to closeout. This review should occur early enough in the project life cycle to allow time for technical assistance and/or the resolution of any corrective actions that may be identified. A desk review should be performed for each administrative consultant and/or Subrecipient soon after the binding agreement has been executed to verify initial performance and identify any technical assistance needs. Additional reviews may be performed to monitor consultants, subrecipients, and/or projects as necessary.

# Monitoring Process

The recommended monitoring process is illustrated below and described in the subsequent sections.

Repeat for each Monitoring Review

## 4.1      Risk Assessment and Monitoring Schedule

Where there is more than one subrecipient, program, or project, risk assessment results are used to determine the priority of monitoring reviews. In cases where a risk assessment is not performed, the basis for determining monitoring prioritization will be documented.

After the initial review, additional program/project monitoring (onsite or desk) should be conducted for all active programs/projects through closeout.

  - Programs/projects requiring follow-up activities and/or corrective actions should take precedence over those not requiring such actions.

  - The program/project risk should also be taken into account when scheduling additional reviews.

See Table 1 for the monitoring schedule. Update Table 1 after the risk assessment is completed.

| Review # | Entity/ Project to Monitor | RA Results | Monitoring Review Date | Desk or Onsite? | Monitor | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Subrecipient | N/A | 10/1/11 | Desk |  |  |
| 2 | Consultant | N/A | 11/1/11 | Desk |  | Ongoing Monitoring Process |
| 3 | Project D | High | 12/1/11 | Onsite |  |  |
| 4 | Project A | High | 2/1/12 | Onsite |  |  |
| 5 | Project E | Low | 4/1/12 | Onsite |  |  |
| 6 | Project B | Medium | 6/1/12 | Onsite |  |  |
| 7 | Project C | Low | 8/1/12 | Onsite |  |  |
| 8 | Project D | High | 10/1/12 | Desk |  |  |
| 9 | Project A | High | 12/1/12 | Desk |  |  |
| 10 | Project B | Medium | 1/15/13 | Desk |  |  |
| 12 | Project C | Low | 4/15/13 | Desk |  |  |

Table 1: Monitoring Schedule

Initial Review

Additional Review of Active Projects Until Closeout

Schedule Guidelines/Tips:

    - At least one onsite review should be conducted of all projects prior to closeout. This review should occur early enough in the project life cycle to allow time for technical assistance and/or the resolution of any corrective actions that may be identified.

      - Projects requiring follow-up activities and/or corrective actions should take precedence over those not requiring such actions.

      - The project risk should also be taken into account when scheduling additional reviews.

    - If a subrecipient has been engaged to administer the project, the subrecipient should monitor the subrecipient soon after the binding agreement has been executed to verify initial performance and identify any technical assistance needs. Follow-up reviews should be performed as necessary.

    - If an administrative consultant has been engaged to administer the project, the subrecipient should begin monitoring the administrative consultant (using the Contract Administration Form) soon after the binding agreement has been executed to verify initial performance and identify any technical assistance needs.  Follow-up reviews should be performed as necessary.

## Execute Checklist

As described within the Monitoring Schedule Table 1, the review will be completed by executing the appropriate checklist. Checklist responses will include comments that detail any issues identified. The executed Checklist will be maintained within the Project file.

## Monitoring Letter

Upon completion of the review, the Monitor will draft a Monitoring Report that identifies the checklist sections used to complete the monitoring review, the results of the review (areas of merit and/or findings or concerns identified, if any), and the basis for the conclusions. The Monitoring Report will be maintained within the appropriate file. If a subrecipient is monitored, the Monitoring Report should be provided to the subrecipient. A Monitoring Report Template is included as Exhibit 11-5 of the LOCD-DR Grant Implementation Manual.

## Technical Assistance

When concerns are identified as a result of the monitoring review, technical assistance may be required to assist in the resolution of the issue. The objective of technical assistance is to ensure compliance with federal, state, and local regulations and program requirements.  The nature and extent of technical assistance should be determined at the discretion of the Monitor, Monitoring Coordinator, Subrecipient, and/or LOCD-DR. Some examples of technical assistance may include:

    - Verbal or written advice;

    - Formal training; and/or,

    - Documentation and guidance.

Evidence of technical assistance should be maintained within the Project file.

The Monitoring Coordinator should contact the LOCD-DR if guidance is required in providing technical assistance to contractors or Subrecipients.

## Follow-up

In the event that findings or concerns are identified for corrective action, follow-up actions should be scheduled to address the progress of the resolution.  The timing and frequency of the follow-up communication should be determined at the discretion of the Monitor and Monitoring Coordinator and should be based on the severity of the deficiency. All follow-up actions should be documented.